## Planning feature
Stage | Tasks
Planing UI | Login [done]
Sign Up [done]
Home Page [done]
List by menu [done]
Detail Material [done]
Add to card
Order Confirm
My profile
Planing Backend | Login
Sign Up
Home Page
List by menu
Detail Material
Add to card
Order Confirm
My profile

## Project milestone
Task | sub task | Team Responsible | Start Date | End Date | Status | Comment
Login | UI login | Duong Dara | 2021-06-01 | 2021-06-02 | Done
| Login connect with firebase | Duong Dara | 2021-07-10 | 2021-07-11 | Done
Sign Up | UI Sign Up | Duong Dara | 2021-06-05 | 2021-06-06 | Done
| Sign Up connect with firebase | Duong Dara | 2021-07-13 | 2021-07-14 | Done
Home Page | List Plants UI | Roeuy Kay | 2021-06-08 | 2021-06-10 | Done
| List Plants connect with firebase | Roeuy Kay | 2021-07-15 | 2021-07-17 | Done
List by menu | Plants | Roeuy Kay | 2021-06-12 | 2021-06-13 | Done
| Planters | Neang Sovanthai | 2021-06-15 | 2021-06-17 | Done
| Tool | Neang Sovanthai | 2021-06-18 | 2021-06-20 | Done
| Décor | Neang Sovanthai | 2021-06-21 | 2021-06-23 | Done
Detail Material | detail material (UI) | Roeuy Kay | 2021-06-26 | 2021-06-29 | Done
| detail material (firebase) | Roeuy Kay | 2021-07-18 | 2021-07-20 | Done
Add to card |  | Neang Sovanthai | 2021-07-21 | 2021-07-23 | Done
Order Confirm |  | Neang Sovanthai | 2021-07-24 | 2021-08-31 | Done
My profile |  | Duong Dara | 2021-07-28 | 2021-08-31 | Done